# Moving ZapTill to our own server — overview for the owner

2026-10-26 · plan only, nothing has been changed yet · the details are in docs/VPS-MIGRATION-PLAN.md and docs/OWN-AUTH-PLAN.md

You asked to leave Supabase's limits behind, host everything on one server costing KES 2,500 a month or less, and build ZapTill's own sign-in at the same time. This is the plan in plain words.

Contents

- What changes

- What stays the same

- Costs

- Timeline

- What you need to buy or do

- Decisions we need from you

# What changes

- One rented server runs the cloud API, the database, the web dashboard (with the web POS) and the admin portal. Recommended: Hetzner CX33 in Germany — 4 processors, 8 GB memory, 80 GB fast disk, 20 TB of traffic — about KES 1,620 a month with Hetzner's daily server backups (about KES 1,880 if 16% VAT is added). If it is sold out that day: Hetzner CAX21 (about KES 1,980), or Contabo Cloud VPS 6 (about KES 1,125).

- No more traffic limits between the API and the database. Today most of the "egress" Supabase counts is our own server asking its own database for data across the internet. On one server that conversation is local and free.

- ZapTill's own sign-in. Owners' and partners' email and password move out of Supabase into ZapTill's own database. ZapTill already makes its own sign-in tokens, second-step codes and reset codes; only the password store and about 35 places in the code that call Supabase change.

- Backups every night (not weekly), encrypted with your passphrase, into your Cloudflare R2 bucket — free, because the copy no longer leaves Supabase. Plus Hetzner's daily server backups.

- Supabase, Render and Vercel are kept untouched for 30 days after the move, then cancelled.

# What stays the same

- Every address: api.zaptill.co.ke, app.zaptill.co.ke, admin.zaptill.co.ke and every client's own address. The website stays on Cloudflare Pages.

- Everyone's password. Passwords are carried over as they are stored today (scrambled, never readable), so nobody has to reset. Most people will not even be signed out.

- The tills. No update is needed. They keep selling offline during the short switch-over and send their sales afterwards.

- M-Pesa. The callback address does not change, so nothing is re-registered with Safaricom.

- Product photos stay on Cloudinary; the shared-components work carries on, and is tested on the new server first.

# Costs

|  | Per month |
| --- | --- |
| Today (Render + Vercel + Supabase Free) | about KES 900–1,800 — but Supabase restricts us from 20 November, and Render suspended production once in October |
| Staying where we are with paid plans (Supabase Pro, Render bandwidth, Vercel Pro for a commercial product) | about KES 6,700–12,100 |
| On our own server (Hetzner CX33 + backups; Cloudflare and R2 free) | about KES 1,620–1,880 |

The price of the saving is looking after the server: automatic security updates, alerts by email and Telegram when something is wrong, and 15 minutes every Monday with a short checklist (the backup is fresh, the disk is not full, no alerts left unanswered). A technician you trust can do it.

# Timeline

Supabase threatens to restrict the free project from 20 November, 25 days from today, so the plan moves production on the night of Sunday 15 → Monday 16 November, at 02:00.

| When | What |
| --- | --- |
| This week (26 Oct – 1 Nov) | You order the server and make the Cloudflare key. We secure the server and set it up. |
| 2 – 8 Nov | The dev environment runs on the new server (with the shared-components branch); ZapTill's own sign-in is built and tested there; the test till T1 points at it. |
| 9 – 15 Nov | A week of using dev on the new server; a full rehearsal with a copy of production; go or no-go on Friday 13 Nov; the switch on Sunday night (about 30 minutes in which tills sell offline and the web POS waits). |
| 16 – 22 Nov | Three days of close watching; the old setup stays ready to switch back. |
| December | Render, Vercel and Supabase cancelled after 30 quiet days. |

If something is late: we can move on the same night with a small copy of Supabase's sign-in service on our server (no code change), and switch to ZapTill's own sign-in a week later. If the whole move slips, one month of Supabase Pro (USD 25) buys time without rushing.

# What you need to buy or do

- Order the server: a Hetzner Cloud account (hetzner.com/cloud; Hetzner may ask for ID), project "ZapTill", server CX33, Ubuntu 24.04, location Nuremberg or Falkenstein, Backups switched on, IPv4 and IPv6 on. Add the SSH public keys we give you (no password login). Send us the server's IP address.

- Cloudflare API token for the certificates: Cloudflare › My Profile › API Tokens › Create token › "Edit zone DNS", zone zaptill.co.ke only. It goes into the server's private settings file, never into email or chat.

- DNS records (we prepare them; you or we switch them on the night): dev-api, app.dev, admin.dev, *.dev now; api, app, admin and * on the night. All "DNS only" (grey cloud).

- Run three short commands in Supabase when we ask (we never connect to it ourselves): the database size, the password format check, and the exports for the rehearsal and the night itself.

- Keep in your password manager: the server's settings file, the backup passphrase, the Hetzner and Cloudflare logins.

- Tell clients who trade at night about the 30-minute window on 15/16 November.

# Decisions we need from you

- Server: Hetzner CX33 (recommended), Hetzner CAX21, or Contabo VPS 6.

- Switch-over night: Sunday 15 → Monday 16 November (recommended); and whether the "small copy of Supabase sign-in" fallback is acceptable that night if ZapTill's own sign-in is not ready.

- Dashboards on the new server (recommended, one place to look after) or on Cloudflare Pages (free, stays up if the server is down).

- Password rule for new passwords: at least 10 characters (recommended) or 12. Existing passwords keep working.

- Backups: nightly at midnight (recommended); and whether to add near-continuous backup (at most 5 minutes of data lost instead of up to a day) in December.

- Who looks after the server each week, and who else may log in to it.

- Supabase Pro for one month as the safety net if the move slips past 20 November.